## Example - SaaS Launch Plan
PROJECT PLAN — SaaS Product Launch
Goal: Launch MVP to 100 paying customers within 120 days ¦ Budget: $25,000 ¦ Owner: Founder / CEO
PHASES & MILESTONES
Phase | Milestone | Start Date | End Date | Duration (days) | Owner | Status
1. Discovery | Problem-solution fit validated | 2026-09-01 | 2026-09-21 | 21 | Founder | Done
2. Design | Clickable prototype approved | 2026-09-22 | 2026-10-05 | 14 | Founder + Designer | Done
3. Build MVP | Product live in staging | 2026-10-06 | 2026-11-09 | 35 | Founder + Dev | In Progress
4. Go-to-Market | Landing page + pricing live | 2026-10-20 | 2026-11-10 | 21 | Founder + Growth | Not Started
5. Launch | 100 paying customers signed | 2026-11-10 | 2026-11-24 | 14 | Whole Team | Not Started
TASK BREAKDOWN
WBS Code
Task
Phase
Owner
Start
End
Status
1.1 | Customer interviews (20) | Discovery | Founder | 2026-09-01 | 2026-09-07 | Done
1.2 | Competitor analysis | Discovery | Founder | 2026-09-08 | 2026-09-12 | Done
1.3 | Validation landing page | Discovery | Founder | 2026-09-13 | 2026-09-21 | Done
2.1 | User story mapping | Design | Founder | 2026-09-22 | 2026-09-25 | Done
2.2 | Wireframes + prototype | Design | Designer | 2026-09-26 | 2026-10-05 | Done
3.1 | Tech stack setup | Build MVP | Dev | 2026-10-06 | 2026-10-08 | Done
3.2 | Auth + user management | Build MVP | Dev | 2026-10-09 | 2026-10-13 | Done
3.3 | Core feature build | Build MVP | Dev | 2026-10-14 | 2026-10-27 | In Progress
3.4 | Billing integration (Stripe) | Build MVP | Dev | 2026-10-20 | 2026-10-24 | Not Started
3.5 | Hosting + deployment | Build MVP | Dev | 2026-10-25 | 2026-10-28 | Done
4.1 | Brand + copy | Go-to-Market | Founder | 2026-10-20 | 2026-10-24 | Done
4.2 | Landing page build | Go-to-Market | Dev | 2026-10-25 | 2026-11-02 | Not Started
4.3 | Onboarding flow + emails | Go-to-Market | Growth | 2026-10-28 | 2026-11-04 | Not Started
5.1 | Beta launch (50 users) | Launch | Founder | 2026-11-10 | 2026-11-16 | Not Started
5.2 | Public launch campaign | Launch | Growth | 2026-11-15 | 2026-11-19 | Not Started
BUDGET
Category
Item
Budgeted
Actual
Variance
Notes
Personnel | Developer (contract) | $10,000 | $8,500 | $1,500 | Part-time remote
Personnel | Designer (contract) | $3,000 | $2,800 | $200 | One-time project
Tools | Software & hosting | $1,500 | $1,200 | $300 | Vercel + Stripe + domain
Marketing | Ads + Product Hunt | $5,000 | $0 | $5,000 | Not started
Buffer | Contingency (15%) | $3,750 | $0 | $3,750 | Reserved
RISK REGISTER
Risk
Probability
Impact
Mitigation
Owner
Status
Core feature takes 2x longer | Medium | High | Scope freeze at MVP; cut nice-to-haves | Founder | Monitoring
Stripe integration blocked | Low | High | Build checkout manually as fallback | Dev | Not Started
Beta users churn >50% | Medium | Medium | Add onboarding checklist + email drip | Growth | Not Started
Launch day traffic spike crashes site | Low | Medium | Load test staging; CDN + caching active | Dev | Done

## Template (Blank)
PROJECT PLAN — [Your Project Name]
Goal: [One-sentence objective] ¦ Budget: [$ amount] ¦ Owner: [Name] ¦ Timeline: [Start] → [End]
PHASES & MILESTONES
Phase | Milestone | Start Date | End Date | Duration (days) | Owner | Status
1. [Phase name] | [Milestone] | [Date] | [Date] |  | [Owner] | Not Started
2. [Phase name] | [Milestone] | [Date] | [Date] |  | [Owner] | Not Started
3. [Phase name] | [Milestone] | [Date] | [Date] |  | [Owner] | Not Started
4. [Phase name] | [Milestone] | [Date] | [Date] |  | [Owner] | Not Started
5. [Phase name] | [Milestone] | [Date] | [Date] |  | [Owner] | Not Started
TASK BREAKDOWN
WBS Code
Task
Phase
Owner
Start
End
Status
[Code] | [Task description] | [Phase] | [Owner] | [Date] | [Date] | Not Started
[Code] | [Task description] | [Phase] | [Owner] | [Date] | [Date] | Not Started
[Code] | [Task description] | [Phase] | [Owner] | [Date] | [Date] | Not Started
[Code] | [Task description] | [Phase] | [Owner] | [Date] | [Date] | Not Started
[Code] | [Task description] | [Phase] | [Owner] | [Date] | [Date] | Not Started
[Code] | [Task description] | [Phase] | [Owner] | [Date] | [Date] | Not Started
[Code] | [Task description] | [Phase] | [Owner] | [Date] | [Date] | Not Started
[Code] | [Task description] | [Phase] | [Owner] | [Date] | [Date] | Not Started
[Code] | [Task description] | [Phase] | [Owner] | [Date] | [Date] | Not Started
BUDGET
Category
Item
Budgeted
Actual
Variance
Notes
[Category] | [Item] |  |  |  | [Notes]
[Category] | [Item] |  |  |  | [Notes]
[Category] | [Item] |  |  |  | [Notes]
[Category] | [Item] |  |  |  | [Notes]
RISK REGISTER
Risk
Probability
Impact
Mitigation
Owner
Status
[Risk description] | [Low/Med/High] | [Low/Med/High] | [Mitigation plan] | [Owner] | Not Started
[Risk description] | [Low/Med/High] | [Low/Med/High] | [Mitigation plan] | [Owner] | Not Started
[Risk description] | [Low/Med/High] | [Low/Med/High] | [Mitigation plan] | [Owner] | Not Started
[Risk description] | [Low/Med/High] | [Low/Med/High] | [Mitigation plan] | [Owner] | Not Started

## How to Build a Plan
HOW TO CREATE A PROJECT PLAN: A 6-STEP GUIDE FOR FOUNDERS
STEP 1: Write the goal in one sentence
A project plan without a clear goal is just a spreadsheet. Write one sentence: 'We will [deliverable] by [date] with [budget].' Example: 'Launch a SaaS product to 100 paying customers within 120 days with a $25,000 budget.'
STEP 2: Break into 4-6 phases
Each phase ends with a milestone you can demo to a stakeholder. Common phases: Discovery, Design, Build, Go-to-Market, Launch, Operations. No phase should overlap. Together they must equal 100% of the project scope.
STEP 3: Decompose phases into tasks
Use a WBS (Work Breakdown Structure) to decompose each phase into tasks. Each task should have one owner, a start date, an end date, and a status. If a task takes more than 2 weeks, break it further.
STEP 4: Build the budget
List every cost category: personnel, tools, marketing, legal, contingency (add 15%). Track budgeted vs actual. Update weekly. The contingency is not 'extra money' — it is insurance against the unexpected.
STEP 5: Identify risks upfront
For each risk, assign probability (Low/Med/High), impact (Low/Med/High), and a mitigation plan. Review the risk register weekly. The risks you identify in week one are cheaper to fix than the ones you discover in week ten.
STEP 6: Review and adapt weekly
A project plan is a living document, not a contract. Review status every week. Update dates, budgets, and risks. If a phase is slipping, decide: cut scope, add resources, or extend timeline. Never do all three.
COMMON MISTAKES
• Planning in too much detail too early. Plan the next phase in detail; future phases at milestone level only.
• No contingency budget. 15% is the minimum for software projects.
• Tasks without owners. If nobody owns it, nobody does it.
• Never updating the plan. A stale plan creates false confidence.
LINK TO WBS
A project plan and a WBS are complementary. The WBS defines WHAT work is in scope. The project plan adds WHEN, WHO, and HOW MUCH. Use the WBS template at theproductivefounder.com/wbs-in-project-management/ to build your scope, then bring it into this project plan template.