## Start here
RACI Matrix Template
One grid, four letters, and every task gets exactly one owner. From theproductivefounder.com
THE FOUR ROLES
R Responsible — does the work. Every task needs at least one R.
A Accountable — owns the outcome, decides, signs off. EXACTLY ONE per task. This is the golden rule.
C Consulted — gives input BEFORE the work (two-way). Keep this list short or decisions stall.
I Informed — told the result AFTER (one-way). Over-using it creates notification noise.
S Support (optional, RASCI variant) — contributes effort or resources without owning the outcome.
HOW TO USE IT
1. On the 'RACI template' sheet, list 5-15 deliverables (not micro-tasks) down the rows.
2. Replace the 'Role 1..6' headers with names (one-off project) or job titles (recurring process).
3. Fill the grid WITH the team, not alone. The matrix is a conversation; the file is a byproduct.
4. Audit: one A per row, at least one R per row, nobody carrying most of the R's, nobody with zero R and zero A.
5. The last column checks every row automatically: OK = exactly one A. FIX = zero or several A's. Do not ignore it.
6. Share it, walk each person through their column, and update the matrix at every phase gate or staffing change.
MISTAKES THAT BREAK A RACI
• Two A's on one row (shared accountability = no accountability).
• Confusing R and A: the doer and the owner are different jobs.
• Too many C's (committee) or too many I's (noise).
• Too much detail: if it is not scannable in 30 seconds, it is a project plan, not a RACI.
• Built in isolation, then never updated. It goes stale in weeks.
PICK THE RIGHT VARIANT
• Tasks and deliverables → RACI (this template). Contributors who help without owning → add S (RASCI).
• Decisions (not tasks) → DACI: Driver, Approver, Contributors, Informed.
• Rare high-stakes calls with real veto power (legal, security, finance) → RAPID.
EXAMPLES INCLUDED
• 'Example — Website redesign': 5-person small business. The founder holds A on every row — allowed, and normal at that size.
• 'Example — Product launch': cross-functional team where A moves from the CEO (strategy rows) to the PM (execution rows).

## RACI template
RACI matrix — your project
Dropdowns: R / A / C / I / S. One A per row — the last column flags violations. Duplicate this sheet per project.
Task / Deliverable | Role 1 | Role 2 | Role 3 | Role 4 | Role 5 | Role 6 | A-count check

## Example — Website redesign
Example — Website redesign (5-person small business)
The founder holds A on every row: normal at this size. One person may own many outcomes — never two owners on one row.
Task / Deliverable | Founder | Designer | Developer | Copywriter | Marketing VA | A-count check
Define goals & sitemap | A | R | C | I | C
Write page copy | A | I | I | R | C
Design mockups | A | R | C | I | I
Develop the site | A | C | R | I | I
Populate content & images | A | C | C | R | R
QA & testing | A | C | R | I | R
Launch & DNS switch | A | I | R | I | I
Post-launch analytics review | A | I | C | I | R

## Example — Product launch
Example — Product launch (cross-functional)
Accountability moves from the CEO (strategy rows) to the PM (execution rows): healthy delegation on paper.
Task / Deliverable | Product Manager | Engineering Lead | Designer | Marketing Manager | Support Lead | CEO | A-count check
Define product requirements | R | C | C | I | I | A
UX / UI design | C | I | R | I | I | A
Build core features | C | R | C | I | I | A
Pricing decision | R | I | I | C | I | A
Launch marketing plan | C | I | C | R | I | A
Support readiness & docs | C | C | I | I | R | A
Go / no-go call | R | C | I | C | C | A
Launch execution | A | R | C | R | C | I