## Example - SaaS Launch
WORK BREAKDOWN STRUCTURE — SaaS Product Launch Example
Source: The Productive Founder (theproductivefounder.com) • Use the 'Template (Blank)' sheet for your own project
WBS Rule: The sum of all work at any level must equal 100% of the project scope. No overlap, no gaps.
WBS Code | Level | Phase / Task | Description | Duration (days) | Owner | Dependencies | Status
1 | 1 | SaaS Product Launch | Complete launch of MVP to first 100 paying customers | 120 | Founder / CEO | — | In Progress
1.1 | 2 | Discovery & Validation | Confirm problem, market, and solution fit | 21 | Founder | — | Done
1.2 | 2 | Design & Prototyping | UX flows, wireframes, and clickable prototype | 14 | Founder + Designer | 1.1 | Done
1.3 | 2 | Build MVP | Core feature set, auth, billing, and hosting | 35 | Founder + Dev | 1.2 | In Progress
1.4 | 2 | Go-to-Market | Landing page, pricing, onboarding, and first traffic | 21 | Founder + Growth | 1.2 | Not Started
1.5 | 2 | Launch & Iterate | Public launch, support, and first feedback loop | 14 | Whole Team | 1.3, 1.4 | Not Started
1.6 | 2 | Post-Launch Operations | Analytics, retention, and roadmap v2 | 15 | Founder + PM | 1.5 | Not Started
1.1.1 | 3 | Customer interviews | 20 interviews with target segment | 7 | Founder | — | Done
1.1.2 | 3 | Competitor analysis | Feature gap and pricing mapping (5 competitors) | 5 | Founder | — | Done
1.1.3 | 3 | Value proposition canvas | Jobs, pains, gains for 2 personas | 4 | Founder | 1.1.1 | Done
1.1.4 | 3 | Validation landing page | Waitlist page with conversion tracking | 5 | Founder | 1.1.3 | Done
1.2.1 | 3 | User story mapping | Core journeys: signup, activation, payment | 4 | Founder + Designer | 1.1.3 | Done
1.2.2 | 3 | Low-fi wireframes | Balsamiq / Figma wireframes for all screens | 5 | Designer | 1.2.1 | Done
1.2.3 | 3 | Clickable prototype | Figma prototype with 3 key user flows | 5 | Designer | 1.2.2 | Done
1.3.1 | 3 | Tech stack setup | Repo, CI/CD, staging, prod environments | 3 | Dev | — | Done
1.3.2 | 3 | Auth & user management | OAuth, email verification, roles | 5 | Dev | 1.3.1 | Done
1.3.3 | 3 | Core feature build | Main value-delivering feature (the 'aha' moment) | 14 | Dev | 1.2.3 | In Progress
1.3.4 | 3 | Billing integration | Stripe: plans, checkout, webhooks, invoice | 5 | Dev | 1.3.2 | Not Started
1.3.5 | 3 | Hosting & deployment | Vercel / AWS / Railway, domain, SSL, monitoring | 4 | Dev | 1.3.1 | Done
1.3.6 | 3 | Internal admin panel | Dashboard for support and user management | 4 | Dev | 1.3.2 | Not Started
1.4.1 | 3 | Brand & copy | Name, tagline, voice, all page copy | 5 | Founder + Growth | 1.1.3 | Done
1.4.2 | 3 | Landing page build | Single high-conversion page with demo video | 7 | Dev + Growth | 1.4.1 | Not Started
1.4.3 | 3 | Pricing page & FAQ | 3-tier pricing, annual discount, FAQ | 3 | Founder | 1.1.2 | Not Started
1.4.4 | 3 | Onboarding flow | In-app checklist + email drip sequence (5 emails) | 6 | Growth | 1.2.3 | Not Started
1.5.1 | 3 | Beta launch | 50 beta users, feedback form, bug triage | 7 | Founder + Support | 1.3.3, 1.4.2 | Not Started
1.5.2 | 3 | Public launch campaign | Product Hunt, HN, Twitter/X, newsletter | 5 | Growth | 1.5.1 | Not Started
1.5.3 | 3 | First 100 customers | Paid acquisition + referral loop target | 7 | Growth | 1.5.2 | Not Started
1.6.1 | 3 | Analytics dashboard | Amplitude / PostHog: activation, churn, LTV | 5 | Founder | 1.3.5 | Not Started
1.6.2 | 3 | Support playbook | FAQ, response templates, escalation rules | 4 | Founder | 1.5.1 | Not Started
1.6.3 | 3 | Roadmap v2 planning | Prioritization framework (RICE), Q2 features | 6 | Founder + PM | 1.6.1 | Not Started
1.3.3.1 | 4 | Database schema | Tables, relations, migrations, seed data | 3 | Dev | 1.3.1 | Done
1.3.3.2 | 4 | API endpoints | REST or GraphQL: CRUD + auth middleware | 4 | Dev | 1.3.3.1 | In Progress
1.3.3.3 | 4 | Frontend screens | React / Vue components with state management | 4 | Dev | 1.3.3.2 | Not Started
1.3.3.4 | 4 | Integration tests | E2E tests for critical user paths | 3 | Dev | 1.3.3.3 | Not Started

## Template (Blank)
WORK BREAKDOWN STRUCTURE — Blank Template
How to use: 1) Replace 'Your Project Name' with your actual project. 2) Break into 4-6 Level-2 phases. 3) Decompose each phase into work packages (Level 3). 4) Break critical work packages into tasks (Level 4).
WBS Rule: Every parent task's scope = 100% of its children's scope combined. No task should take longer than 2 weeks at Level 4.
WBS Code | Level | Phase / Task | Description | Duration (days) | Owner | Dependencies | Status
1 | 1 | Your Project Name | Project description here |  |  | — | Not Started
1.1 | 2 | Phase 1: [Name] | Phase description |  |  | — | Not Started
1.1.1 | 3 | Work package 1.1 | Description |  |  | — | Not Started
1.1.2 | 3 | Work package 1.2 | Description |  |  | — | Not Started
1.2 | 2 | Phase 2: [Name] | Phase description |  |  | — | Not Started
1.2.1 | 3 | Work package 2.1 | Description |  |  | — | Not Started
1.2.2 | 3 | Work package 2.2 | Description |  |  | — | Not Started
1.2.2.1 | 4 | Task A | Sub-task description |  |  | — | Not Started
1.2.2.2 | 4 | Task B | Sub-task description |  |  | — | Not Started
1.3 | 2 | Phase 3: [Name] | Phase description |  |  | — | Not Started
1.3.1 | 3 | Work package 3.1 | Description |  |  | — | Not Started
1.4 | 2 | Phase 4: [Name] | Phase description |  |  | — | Not Started
1.4.1 | 3 | Work package 4.1 | Description |  |  | — | Not Started
1.5 | 2 | Phase 5: [Name] | Phase description |  |  | — | Not Started
1.5.1 | 3 | Work package 5.1 | Description |  |  | — | Not Started
1.6 | 2 | Phase 6: [Name] | Phase description |  |  | — | Not Started
1.6.1 | 3 | Work package 6.1 | Description |  |  | — | Not Started

## How to Build a WBS
WORK BREAKDOWN STRUCTURE: A 5-Step Guide for Founders
STEP 1: Define the Project Scope
Write one sentence that describes 100% of what this project delivers. If you cannot say it in one sentence, you do not know the scope yet. Example: 'Launch a SaaS product to 100 paying customers within 4 months.'
STEP 2: Identify Major Phases (Level 2)
Break the project into 4-6 major phases. Each phase is a large chunk of work that produces a measurable deliverable. Common phases for a founder: Discovery, Design, Build, Marketing, Launch, Operations.
Rule: The sum of all Level-2 phases must equal 100% of the project. No overlap. No gaps.
STEP 3: Decompose into Work Packages (Level 3)
Each phase breaks into 2-5 work packages. A work package is a deliverable or outcome, not an activity. Example: 'Billing integration' (outcome) not 'Code Stripe API' (activity).
Rule: Each work package should be assignable to one person and estimable in days (ideally 5-15 days).
STEP 4: Break into Tasks (Level 4)
Only decompose work packages that are complex, risky, or unfamiliar. A task should take 1-3 days. If a task takes more than 2 weeks, break it further. Stop when the team can estimate and assign confidently.
STEP 5: Validate the 100% Rule
For every parent task, ask: 'Does the sum of my children equal 100% of the parent, with nothing extra and nothing missing?' If yes, your WBS is structurally sound. If no, fix the gaps or overlaps before you start work.
COMMON MISTAKES
• Mixing phases and tasks at the same level. Keep hierarchy consistent.
• Making a WBS a todo list. A WBS decomposes deliverables, not actions.
• Stopping at Level 2. Most projects need at least Level 3 to be useful.
• Forgetting dependencies. A WBS without dependencies is just a list.
WBS vs Gantt vs RACI
• WBS = WHAT work needs to be done (scope decomposition)
• Gantt = WHEN the work happens (schedule with timeline)
• RACI = WHO does what and who decides (roles & responsibilities)
Use all three together for complete project control. Get the RACI template at theproductivefounder.com.